## Sheet1
STT | Feature | Sub-feature | Flow / Behavior Description | Status | PIC | Deadline
1 | STRATEGY & MATH ENGINE |  |  | In Progress | duy.nguyen6
2 | AMM position math | L ↔ amounts | getLiquidityForAmounts (inverse) + getAmountsForLiquidity (forward). | In Progress | duy.nguyen6
3 |  | lpEthAmount + IL | ETH held in LP at a given price; impermanent loss vs HODL. | In Progress | duy.nguyen6
4 | Hedge math & sizing | computeTargetShort (seam) | targetShort = lpEth × ratio. zen formula still placeholder. | In Progress | duy.nguyen6
5 |  | delta + hedgeStepPnl | delta = target − actual; step PnL = price move + funding. | In Progress | duy.nguyen6
6 | Margin & liquidation | requiredMargin / liquidationPrice | Isolated margin; add maintenance-margin buffer (zen). | In Progress | duy.nguyen6
7 |  | preflight margin check | Pure fn → {ok, marginNeeded, shortfall} before start. | In Progress | duy.nguyen6
8 | 8-trigger evaluation | evaluateTriggers(state)→decision | drift abs/rel, range_out, range_boundary_near, margin_warning, funding_alert, time_fallback, manual, recovery. | In Progress | duy.nguyen6
9 | Economic gate / budget cap | hedge budget cap | Block rebalance when hedge cost > 30% trailing-7d LP fee → pause/reduce. | In Progress | duy.nguyen6
10 | HYPERLIQUID INTEGRATION (hedge leg) |  |  | Todo | duy.nguyen6
11 | HL SDK spike | Workers compat test | @nktkas/hyperliquid read call in Worker → decide SDK vs custom HTTP+viem. Blocker for whole hedge leg. | Todo | luong.tran
12 | Live adapter + signing | EIP-712 signing | Sign order with viem, chainId 42161. | Todo | duy.nguyen6
13 |  | exchange POST + errors | POST /exchange; handle nested HL error format. Replace DryHyperliquidAdapter. | Todo | duy.nguyen6
14 | Order / stop / reconcile | IOC delta-only order | reduce-only / increase by delta; full close on target=0. | Todo | duy.nguyen6
15 |  | native stop-loss | reduce-only stop + stop_cloid / stop_price_usd. | Todo | duy.nguyen6
16 |  | post-order reconcile + cloid | Re-read HL position, fix drift; cloid idempotency. | Todo | duy.nguyen6
17 |  | funding tracking | Read/record funding cost/income of short. | Todo | duy.nguyen6
18 | Agent key encryption | envelope encrypt/decrypt | AES-GCM (crypto.subtle); DEK wrapped by master key (Secrets Store). | Todo | duy.nguyen6
19 |  | master key rotation | Re-wrap DEK, set rotated_from + key version. | Todo | duy.nguyen6
20 | Rate limiting (HLRateLimitDO) | sliding-window reserve | By HL weight; return reserved:false + retryAfterMs when over. | Todo | duy.nguyen6
21 | HL testnet validation | end-to-end testnet | Agent key → IOC short → stop → read fill → reduce-only close. | Todo | duy.nguyen6
22 | BOT ORCHESTRATION & RUNTIME |  |  | Todo | duy.nguyen6
23 | Cron scan + queue fan-out | cron + jitter producer | Tick per active bot → enqueue bot-scan. | Todo | duy.nguyen6
24 |  | 8 queues + DLQ wiring | bot-scan/light-check/hedge-sync/reconcile/deep-audit/stop-audit/notification/metrics-rollup. Handlers currently no-op. | Todo | duy.nguyen6
25 | Scan & light-check consumer | read LP + HL state | Alchemy LP + HL state → compute lpEth/targetShort/deltaError. | Todo | duy.nguyen6
26 |  | evaluate triggers → route | Trigger eval on cache (no HL) → route to next queue. | Todo | duy.nguyen6
27 | Hedge-sync & reconcile consumer | lock + reserve + adjust | Lock → reserve rate → delta-only adjust (batch=1). | Todo | duy.nguyen6
28 |  | poll fill + reconcile | Poll fill → compare actual vs expected → flag mismatch. | Todo | duy.nguyen6
29 | Stop-audit & SAFE_MODE | verify stop order | fill / pending / missing. | Todo | duy.nguyen6
30 |  | SAFE_MODE freeze + alert | Freeze hedge, scan keeps running, alert until admin clears. | Todo | duy.nguyen6
31 | Lifecycle state machine | transition table + guards | idle→LP_OPENING→active→LP_REBALANCING→active→closing→closed; safe_mode/LP_FAILURE. | Todo | duy.nguyen6
32 |  | write D1 + notification | Persist transition + bump updated_at + enqueue notification. | Todo | duy.nguyen6
33 | Durable Objects | UserLockDO lease | 1 bot/user, no overlapping cycle. | Todo | duy.nguyen6
34 |  | MarketDataDO cache | Price/tick snapshot for light-check. | Todo | duy.nguyen6
35 | D1 schema & repositories | tables + repos | bots, bot_runtime_state, hedge_legs, hl_agent_keys, queue_idempotency. | Todo | duy.nguyen6
36 |  | optimistic concurrency | state_version guard against stale writes. | Todo | duy.nguyen6
37 | VAULT SMART CONTRACT (BnzaExVault.sol) |  |  | Todo | truong.nguyen2
38 | Core custody functions | vaultMint / vaultClose | Mint LP NFT into vault; close → return tokens + payout. | Todo | truong.nguyen2
39 |  | vaultRebalance | Atomic close→swap→mint new NFT, vault keeps custody. | Todo | truong.nguyen2
40 |  | collectFees | Collect LP fees. | Todo | truong.nguyen2
41 | Access control | onlyOperator mutations | Pattern BnzaLpBot; only relayer Worker. | Todo | truong.nguyen2
42 |  | EMERGENCY_ROLE multi-sig | Gnosis Safe / AccessControl (pattern BNZAToken). | Todo | truong.nguyen2
43 | Emergency controls | emergencyTransfer / pause / rotateOperator | Emergency role only. | Todo | truong.nguyen2
44 | Tests (unit + fork) | Foundry unit | Mock NPM/Router custody flow. | Todo | truong.nguyen2
45 |  | fork test Base/OP | Real Uniswap V3 flow. | Todo | truong.nguyen2
46 | Deploy & verify (manual) | Sepolia → audit → mainnet | Basescan verify; zen confirms operator + multi-sig. | Todo | truong.nguyen2
47 | Vault client (off-chain) | LiveBnzaExVaultClient | viem calls post-deploy; replaces dry client. | Todo | truong.nguyen2
48 | OPERATOR FACADE & API |  |  | Todo | duy.nguyen11
49 | Facade routes | /api/exbot/* proxy | start/status/close/agent-key/margin → EXBOT internal. | Todo | duy.nguyen11
50 | Auth & transport | accessControl + auth_context | Server-side wallet/role; no client escalation. | Todo | duy.nguyen11
51 |  | service binding + internal token | Worker→Worker; EXBOT not public. | Todo | duy.nguyen11
52 | Real internal API | start/close → orchestration | Open/close LP+short instead of dry stub. | Todo | duy.nguyen11
53 |  | margin preflight + agent-key | Real margin check; real agent-key store. | Todo | duy.nguyen11
54 | POOL UI — EXBOT |  |  | Todo | duy.nguyen11
55 | Start ExBot | balance form + APR estimate | Initial balance input + backtest APR preview. | Todo | duy.nguyen11
56 |  | agent-key approval | Approve/submit HL agent key flow. | Todo | duy.nguyen11
57 | ExBot Status | positions + margin health | LP position, hedge position, margin status. | Todo | duy.nguyen11
58 |  | cumulative PnL | Running net PnL view. | Todo | duy.nguyen11
59 | Close ExBot | confirm + settlement preview | Confirm close + show settlement. | Todo | duy.nguyen11
60 | BACKTEST |  |  | Todo | trung.hoang
61 | Core engine + report | ReplayProvider + simulators | SQLite → frames → lp-sim + hedge-sim. | Todo | trung.hoang
62 |  | runBacktestOnFrames + metrics | Pure runner → report + Sharpe/drawdown/APR. | Todo | trung.hoang
63 | CLI / API / UI | bnza-backtest-cli/api/ui | All three working. | Todo | trung.hoang
64 | Crawl Base + OP dataset | set keys + run crawl | GRAPH_API_KEY + POOL_ADDRESS → crawl → SQLite. OP dataset already done. | Todo | trung.hoang
65 | Accurate fee model | feeGrowthGlobal fee | Replace volume approximation in lp-simulator. | Todo | trung.hoang
66 | Multi-core param sweep | worker_threads grid | Sweep range/hedge%/leverage → comparison table. | Todo | trung.hoang
67 | Web deploy + compare (no Electron) | deploy backtest web (API/UI) | Host web UI + API (Fly.io/Vercel) for internal use. | Todo | trung.hoang
68 |  | multi-pool compare UI | Overlay Base vs OP on same config. | Todo | trung.hoang
69 |  | dataset → R2 upload | Push .sqlite to R2 for shared access. | Todo | trung.hoang
70 | INFRA, CI/CD & DEVOPS |  |  | Todo | duy.nguyen11
71 | Cloudflare provisioning | D1 + 8 queues + Secrets | HL_MASTER_KEY, EXBOT_INTERNAL_AUTH_TOKEN, ALCHEMY (staging→prod). | Todo | duy.nguyen11
72 |  | replace fake IDs | Fill real IDs in wrangler.toml. | Todo | duy.nguyen11
73 | CI — per-package test gates | add tests to ci.yml | test for @bnza/exbot, shared-position-math, backtest-engine. | In progress | duy.nguyen11
74 | CD — EXBOT Worker | deploy job | path trigger apps/bnza-exbot/** → wrangler deploy --env + D1 migrate + secrets. | Todo | duy.nguyen11
75 | CD — Crawler (scheduled) | cron job | GH Action/container: crawl → export SQLite → upload R2. | Todo | duy.nguyen11
76 | CD — Backtest web | host + build | Fly.io/Vercel + native better-sqlite3 build step. | Todo | duy.nguyen11
77 | Environments & secrets | GH environments | dev/staging/prod secret sets for EXBOT + crawler. | In progress | duy.nguyen11
78 | Rollback & monitoring | rollback + smoke + logpush | wrangler rollback, tail-worker hook, deploy smoke check. | Todo | duy.nguyen11